## Roles
PAYSAFE · KONG API & AI GATEWAY ADOPTION | [5 empty] | Roles & Involvement Map
Confidential · v1.0 · June 2026
Role | Team | Type | FTE | P1 | P2 | P3 | P4 | P5 | RACI Mig. | RACI Ops | Responsibility
Programme Sponsor (CTO) | Exec Leadership | Exec | 0.1 | ● | ● | ● | ● | ● | A | I | Owns outcomes; unlocks budget; chairs Steering Committee; resolves exec escalations.
Head of Platform Eng. | Platform Eng. | Lead | 0.5 | ● | ● | ● | ● | ● | A | A | Platform ownership; Kong vendor relationship; major incident escalation; roadmap.
Programme Manager | PMO | Delivery | 1.0 | ● | ● | ● | ● | ● | R | I | Governance; sprint planning; RAID log; status reporting; cross-squad dependencies.
API Platform Eng. (Kong SME) | Platform Eng. | Eng | 2-3 | ● | ● | ● | ● | ● | R | R | Konnect config; K8s data-plane; plugin dev (Lua/Go); decK/Terraform IaC.
External Kong SE | Vendor | Contract | 1.0 | ● | ● | ● | – | – | C | C | Best-practice guidance; knowledge transfer; complex troubleshooting; ramp-up.
API Architect | Architecture | Arch | 1.0 | ● | ● | ● | ● | ● | A | C | API design standards; OAS governance; onboarding approvals; tech evaluation.
Solution Architect (Payments) | Architecture | Arch | 1.0 | ● | ● | ● | ● | ● | C | C | Payment migration design; PCI-DSS architecture validation; cutover sign-off.
Site Reliability Eng. (SRE) | Platform Ops | Ops | 2-3 | ● | ● | ● | ● | ● | R | A | On-call; incident response; SLO monitoring; capacity planning; rollback execution.
Security Engineer | Security | Sec | 1-2 | ● | ● | ● | ● | ● | A | I | PCI-DSS controls; WAF policy; Vault secrets; pen-test coordination; sign-off gates.
Compliance / QSA Liaison | Risk & Compliance | Comp | 0.25 | – | ● | ● | ● | – | C | I | QSA liaison; PCI re-cert scope; audit evidence collection for regulators.
DevOps / IaC Engineer | Platform Eng. | Eng | 1.0 | ● | ● | ● | ● | ● | R | R | Terraform modules; ArgoCD/GitOps; CI/CD integration; environment provisioning.
AI/ML Gateway Engineer | AI/ML Eng. | Eng | 0.5-2 | ● | ● | – | ● | ● | R | R | AI Proxy config; LLM provider integration; semantic cache tuning; prompt policy.
Data/ML Platform Lead | AI/ML Eng. | Lead | 0.25 | – | ● | – | ● | ● | C | C | AI Gateway requirements; token cost controls; model routing/fallback approval.
Product Eng. Squad Lead | Product Eng. | Eng | 0.3-1 | – | ● | ● | ● | ● | R | C | Owns squad migration execution; API requirements; self-service onboarding.
Backend / API Developer | Product Eng. | Eng | 2-6 | – | ● | ● | ● | – | R | I | Implements contract changes; supports canary validation; fixes integration issues.
QA / Test Engineer | Quality Eng. | Eng | 1-2 | ● | ● | ● | ● | – | R | I | Contract/load testing (k6); security scans (ZAP); validates canary SLO thresholds.
Product Manager (Platform) | Platform Product | Prod | 0.5-1 | ● | ● | ● | ● | ● | C | C | Dev portal roadmap; self-service UX; developer NPS; feature prioritisation.
Tech Writer / Dev Advocate | Platform Product | Support | 0.5 | ● | ● | ● | ● | ● | I | I | Portal content; migration guides; API docs; prompt-engineering guides; training.
Partner Integration Manager | Partner Mgmt | Biz | 0.5-1 | – | – | ● | ● | – | C | I | 90-day partner notices; sandbox onboarding; partner escalations during cutover.
FinOps Analyst | Finance | Fin | 0.25 | – | ● | ● | ● | ● | I | C | Tracks infra/licence cost vs budget; AI token spend; TCO savings reporting.
Network Engineer | Infrastructure | Eng | 0.25-0.5 | ● | ● | ● | – | – | C | C | DNS/weighted routing for canary & rollback; VPC/network policy; CDN/WAF integration.
● Full involvement ● Partial involvement – Not involved ¦ RACI: R Responsible · A Accountable · C Consulted · I Informed ¦ P1 Foundation (M1-3) · P2 Pilot Migration (M3-6) · P3 Payment APIs (M6-12) · P4 AI Gateway/Decom (M12-15) · P5 Optimisation (M15-18)